## Master Checklist
ID | Checklist item / accomplished scope | Status | Current note
Authentication
AUTH-01–10 | Invite-only login, invitations, verification, MFA, sessions, roles, reauthentication, and secure role grants. | Done | Beta hardening completed: only Super Admin can grant or revoke administrator roles, manage administrator accounts, or change system security settings. Backend authorization blocks direct API bypass. Temporary-password accounts must replace the password before protected access.
AUTH-11 | Full invite, password-reset, MFA, suspension, and role-change regression pass. | Done
Ticket Management
TKT-01–16 | Ticket creation through closure, notes, requester updates, ownership lock, Super Admin override, and AI restrictions. | Done | Beta hardening completed: user-scoped counters now separate Open, In Progress, Resolved, Closed, and Total. Backend rules enforce Open → In Progress → Resolved → Closed and Resolved → In Progress. Resolution notes, history, and secure authenticated PNG/JPEG/WebP attachments are preserved.
Service Level Agreements
SLA-01–07 | 24/7 SLA timing, risk scoring, warning alerts, and breach events. | Done
SLA-08 | SLA targets remain configurable by authorized Super Admins in Settings. | N/A | Separate fixed-policy confirmation is not applicable because authorized Super Admins manage SLA targets in the web app.
Notifications and Operational Feed
NTF-01–09 | Live operational feed, multi-admin notifications, pagination, filtering, and retention configuration. | Done
NTF-10 / QA-16 | Confirm scheduled notification retention cleanup with real elapsed data. | Done | User-confirmed retention acceptance passed after Beta was used solely for development and validation.
Collectors and Monitoring
COL-01–18 | Enrollment, telemetry, discovery, refresh, repair, revocation, deduplication, and dynamic-IP support. | Done | Includes two-device acceptance, revoked collector rejection, and dynamic-IP deduplication. The collector release remains HTTPS-hosted, SHA-256-pinned, scope-authorized, and free of localhost or machine-specific paths. Automated portability checks passed; a separate-PC install remains a manual acceptance test.
COL-19–20 | Collector update policy and possible macOS/Linux support. | After launch
AI Assistance
AI-01–09 | Fallback assistance, Ollama Bridge architecture, local-only model approach, and Gemini removal from Beta. | Done
Inventory
INV-01–05 | Inventory, device details, readable drive data, and identity consolidation. | Done
Knowledge Base, Collaboration, and User Experience
KB-01 | Knowledge base baseline. | Done
KB-02 | Automatically detect recurring resolved issues and create a reviewable knowledge-base candidate after three similar occurrences. | Done | Beta PR #27 verified on revision aitsm-beta-00083-zel. Three unique similar resolved tickets create a traceable candidate; Super Admin review is required before publication.
COLLAB-01 | Chat and colleagues baseline. | Done
UX-01–03 | Responsive navigation and UI cleanup. | Done
UX-04–06 | Accessibility, responsive testing, and Beta feedback process. | Done | User-confirmed accessibility, responsive behavior, and Beta feedback checks passed.
Security
SEC-01–06 | HTTPS, RBAC, reauthentication, secrets, scanning, and audit logging. | Done
SEC-07 | Final public-repository review for historical sensitive data and configuration. | Done | Public main source, remote branch names, recent commit messages, releases, and deployment metadata were reviewed; no unwanted branding or open GitHub security alerts remain.
SEC-08 | Focused review of authentication, collector enrollment, uploads, and AI Bridge. | Done | Focused production review completed. Protected tests, dependency and secret scans, and CodeQL passed. The new RBAC boundaries, attachment authorization, image decoding, and mandatory-password middleware also passed protected review on PR #9.
Quality Assurance
QA-01–15, QA-18 | Automated checks and completed Beta functional validation. | Done | 111 automated tests passed. JavaScript syntax, dependency scanning with zero reported vulnerabilities, secret scanning, and Java/Kotlin and JavaScript CodeQL passed. Beta smoke tests returned HTTP 200. Manual acceptance remains for the two-role UI, browser attachment flow, forced-password flow, and separate-PC collector installation.
QA-17 | Browser-level end-to-end regression pass. | Done | User-confirmed browser-level regression passed.
Source Control and Release Engineering
SCM-01–04 | GitHub branch organization, protection, security scanning, and source cleanup. | Done
REL-01–05 | GitHub-to-Google Cloud pipeline, migrations, health checks, rollback path, and Beta deployment. | Done | Six-issue Beta hardening is live on revision aitsm-beta-00052-waz from commit 569d2aa12b684ee9bdc4a084427430fedb4c0323. Three post-promotion health checks returned HTTP 200, legacy Gemini variables remain absent, and the prior revision is retained for rollback.
Production Release
PROD-02 | Production Cloud SQL backup completed successfully. | Done | Backup 1792325031222.
PROD-03 | Final Beta log, stability, and cost review. | Done | Final Beta security and deployment run 39454166237 passed. Revision aitsm-beta-00044-bes returned HTTP 200 with zero legacy Gemini environment variables.
PROD-04 | Create the protected beta → main release pull request. | Done | Protected release PR #5 was merged from beta to main after the verified Beta deployment.
PROD-05 | Approve production deployment. | Done | Protected production deployment approval was recorded after all required security checks passed.
PROD-06 | Production smoke test. | Done | Production run 39503798792 passed. Revision aitsm-00048-luf serves 100% of traffic; health and landing-page smoke tests both returned HTTP 200.
PROD-07 | Confirm rollback revision availability. | Done | Previous live revision aitsm-00035-fz5 remains Ready and available as the verified rollback target.
PROD-08 | Remove legacy Gemini provider/key configuration from production and apply the Beta Ollama/fallback configuration. | Done | Production revision aitsm-00048-luf contains OLLAMA_MODEL=qwen3:8b and zero AI_PROVIDER, GEMINI_MODEL, or GEMINI_API_KEY variables.
Operations
OPS-01 | Document and verify the production database restoration procedure. | Done | Backup 1792325031222 was restored to temporary PostgreSQL 16 instance aitsm-restore-drill-20261021. The instance was RUNNABLE, the restored production database exposed 27 public tables, and read-only users/tickets queries succeeded. The temporary instance was deleted; production and the backup remain healthy.
OPS-02 | Configure the Google Cloud monthly budget alert. | Done | Monthly $100 credit guardrail configured.
OPS-03 | Configure Google Cloud budget alerts and error alerts. | Done | Budget guardrail and production Cloud Run 5xx email alert configured.
Analytics
ANA-01–02 | Validate analytics with production-scale data and define reports. | After launch | ANA-02 will be checked after operational deployment using live data. ANA-01 remains part of the production-scale validation.